## Decision Log
Date | Time | Problem | Considered Options | Chosen Option | Reason for Choice | Status | Changelog Reference
18.07.2026 | 02:00 | Post-processing pipeline structure | 1) Modular pipeline with 6 components 2) Monolith script 3) Use existing aniposelib | Modular pipeline with 6 components | Testability of each module, ability to replace individual components | Completed | changelog: 18.07.2026 02:00
18.07.2026 | 11:00 | Cubic spline interpolation creates wild oscillations on gaps | 1) Keep cubic spline 2) Linear interpolation 3) NN-based filling (DNO/StableMotion) 4) Bone-aware filling | Linear interpolation | Guaranteed to stay within bounds of support points, simple and fast. NN-based deferred until basic stabilization. | Completed | changelog: 18.07.2026 11:00
18.07.2026 | 11:30 | IK after NaN filling loses effectiveness | 1) Gap fill → Filter → Bones → Feet (was) 2) Outlier → Bones → Gap fill → Filter → Bones → Feet 3) Gap fill → Bones → Filter → Feet | Order: Outlier → Gap fill → Filter → Bones → Feet | IK works on valid data before interpolation, second pass after filtering | Completed | changelog: 18.07.2026 11:30
18.07.2026 | 12:00 | Non-rigid bones (foot_index) worsen IK results | 1) All 14 bones 2) 10 rigid only (8 limbs + 2 heels) 3) 8 rigid only (no heels) 4) Per-bone custom thresholds | 8 rigid bones (limbs), no heels or cross-body | Heels are small and noisy, foot_index is non-rigid. Focus on main limb segments. | Completed | changelog: 18.07.2026 12:00
18.07.2026 | 13:00 | Iterative relaxation oscillates and diverges | 1) Gauss-Seidel relaxation (lr=0.5, 10 iter) 2) Iterative projection (lr=0.3, 5 iter) 3) FK-BFS (single-pass tree traversal from roots) 4) DLS (Damped Least Squares) 5) CCD (Cyclic Coordinate Descent) | FK-BFS — single-pass tree traversal from roots | Guaranteed convergence, O(n), exact bone lengths for corrected bones. DLS/CCD more complex with no advantage in this context. | Completed | changelog: 18.07.2026 13:00
18.07.2026 | 14:00 | FK-BFS moves ankle but heel/foot_index stay in place | 1) Leave as is (don't touch heel) 2) Propagate offset from ankle to heel/foot_index 3) Run FK-BFS from heel too | Offset propagation: non_rigid_children shifted by same vector | Simple solution, preserves relative positioning. Alternatives more complex with no significant advantage. | Completed | changelog: 18.07.2026 14:00
18.07.2026 | 14:06 | Need to maintain project documentation in two languages | 1) Markdown only 2) xlsx for tables + md for log + docx for report 3) Confluence/Notion | Markdown for log, xlsx for decision tables, docx for technical report | Universal format, no special tools needed, easy to version in git | Completed | changelog: 18.07.2026 14:06
18.07.2026 | 14:30 | Filters destroy bone lengths, OneEuro fills NaN with fake data | 1) Reduce Butterworth order (4->2) 2) Increase IK tolerance to 50% 3) Fix OneEuro: preserve NaN 4) Add bone-aware filter 5) Double IK (before and after filter) | Combination: OneEuro preserves NaN + BW order=2 + double IK (30% + 50%) | Combination gave best results: average CoV reduced by 75.7% vs original. Bone-aware filter is research direction, requires more work. | Resolved | changelog: 18.07.2026 14:30
18.07.2026 | 14:45 | Problems 7-14: which are actionable from post-processing? | 1) All 8 problems 2) Only 8, 10, 14 (post-processing) 3) None — require re-capture 4) Only 10 (floor plane) | Diagnostic modules for 8, 10, 14 + honest limitation description | Of 8 problems only 3 are actionable from post-processing. 7,9,11,13 require re-capture. 12 is downstream. | Resolved | changelog: 18.07.2026 14:45
18.07.2026 | 15:00 | Problem 8: Z-axis filtering needs different parameters than XY | 1) Same cutoff for all axes 2) Z gets higher cutoff (less smoothing) 3) Z gets lower cutoff (more smoothing) 4) Separate filter per axis group | Z gets higher cutoff (z_cutoff_ratio=1.5) | Z axis has higher triangulation noise but also more real depth variation. Less smoothing preserves real signal while XY smoothing handles lateral jitter. | Completed | changelog: 18.07.2026 15:00
18.07.2026 | 15:30 | Problem 3: Independent interpolation of foot markers creates inconsistent bone lengths | 1) Ignore (let IK fix later) 2) Median offset re-anchoring from ankle 3) FK-BFS re-enforcement after gap fill 4) Spline interpolation with bone constraints | Median offset re-anchoring from ankle | Simple median-based approach, robust to outliers, corrects foot bone consistency immediately after interpolation before IK runs. | Completed | changelog: 18.07.2026 15:30
18.07.2026 | 16:00 | Problem 6: Body/hand wrist boundary mismatch | 1) Ignore (too complex) 2) Snap hand to body wrist (body_wins) 3) Snap body to hand wrist (hand_wins) 4) Average both | Snap hand to body wrist (body_wins) | Body wrist is more reliable (less noise, more tracking frames). Moving entire hand by same offset preserves hand internal consistency. | Completed | changelog: 18.07.2026 16:00
18.07.2026 | 16:30 | Problem 10: Floor plane alignment integration | 1) Always align (breaking change) 2) Optional parameter (align_floor) 3) Separate post-processing script 4) Auto-detect if needed | Optional parameter (align_floor=False default) | Non-breaking: existing workflows unaffected. User must explicitly enable. Floor alignment only useful when foot data is clean. | Completed | changelog: 18.07.2026 16:30
18.07.2026 | 17:00 | Pipeline v3 stage ordering | 1) 7 stages (original) 2) 8 stages with foot gap correction before IK 3) 9 stages with separate hand/face filter stages 4) Dynamic ordering based on data quality | 8 stages with foot gap correction at 3.5 | Foot gap correction must run after gap fill and before IK. Inserting at 3.5 preserves existing stage numbers while adding critical foot consistency fix. | Completed | changelog: 18.07.2026 17:00
18.07.2026 | 19:45 | RTMPose output format handling | 1) Assume dict format with body/hands/face keys 2) Handle tuple format with segment splitting 3) Use wrapper function to normalize output | Handle tuple format with segment splitting | RTMPose Wholebody3d returns tuple (keypoints_3d, scores, refined, kpts2d). Segment splitting by indices [0:17] body, [17:23] feet, [23:91] face, [91:112] L-hand, [112:133] R-hand. Dict format was incorrect assumption. | Completed | changelog: 18.07.2026 19:45
18.07.2026 | 19:45 | RTMPose pixel vs world coordinates | 1) Convert RTMPose pixel coords to world using camera calibration 2) Accept as 2D+depth tracker, no direct comparison with MediaPipe 3) Run multi-camera RTMPose + DLT triangulation | Accept as 2D+depth tracker for now (option 2) | Camera calibration data not available. Multi-camera RTMPose requires additional infrastructure. RTMPose provides usable tracking data in pixel space. Direct numerical comparison with MediaPipe world coords is meaningless without calibration. | Partial — requires calibration for world coords | changelog: 18.07.2026 19:45
18.07.2026 | 20:00 | Self-occlusion detection approach | 1) Cross-camera keypoint comparison 2) Per-joint confidence consistency check 3) Temporal anomaly detection on single camera | Cross-camera keypoint comparison (option 1) | Multi-camera is the only reliable way to distinguish correct from incorrect confident detections. Single-camera methods cannot distinguish self-occlusion from real fast motion. | Completed | changelog: 18.07.2026 20:00
18.07.2026 | 20:15 | Motion blur handling strategy | 1) Deblur preprocessing before MediaPipe 2) Detect and skip blurry frames 3) Detect only, flag for manual review | Detect and evaluate (options 2+3 combined) | Deblur models risk creating artifacts worse than original blur. Detection + quality correlation gives actionable info without modifying input data. | Completed | changelog: 18.07.2026 20:15
18.07.2026 | 20:30 | Calibration drift detection method | 1) Reprojection error monitoring (with calibration) 2) Trajectory smoothness monitoring (without calibration) 3) Both modes in one function | Both modes in one function (option 3) | Different use cases: with calibration = precise per-camera detection; without = general anomaly detection. Single function with automatic mode selection. | Completed | changelog: 18.07.2026 20:30
18.07.2026 | 21:00 | Distortion weighting formula | 1) Distance-from-center power law 2) Actual lens distortion profile (Brown-Conrady) 3) Empirical lookup table from calibration | Distance-from-center power law (option 1) | No lens distortion profile available. Power law is a good proxy that captures the key insight: edge keypoints are less reliable. Parameterizable. | Completed | changelog: 18.07.2026 21:00
18.07.2026 | 21:15 | Camera coverage visualization approach | 1) 2D floor grid with frustum test 2) 3D voxel grid with ray casting 3) Analytical overlap volume calculation | 2D floor grid (option 1) | Actors are upright, floor-level coverage is most relevant. 2D grid is simple, fast, and sufficient for planning. ASCII output for quick terminal assessment. | Completed | changelog: 18.07.2026 21:15
18.07.2026 | 22:00 | Module import style (relative vs absolute) | 1) Keep relative imports (from .module) 2) Convert to absolute imports (from module) 3) Conditional imports with fallback | Absolute imports (option 2) | Relative imports break when modules are imported standalone for testing. Absolute imports work both as package and standalone. 20 imports converted across 14 files. No functional change when running as package. | Completed | changelog: 18.07.2026 22:00
18.07.2026 | 22:00 | ensemble_hands NaN blending strategy | 1) Keep broken NaN arithmetic (1-w)*NaN+w*data=NaN 2) Replace NaN with 0 before blend, restore NaN where both NaN 3) Separate branches: if MP valid blend, if MP NaN use RT, if both NaN keep NaN | Option 2: np.where NaN handling | Simpler than branching, works per-keypoint. (1-w)*0+w*data = w*data when MP is NaN. NaN restored where both sources are NaN. No performance overhead. | Completed | changelog: 18.07.2026 22:00
18.07.2026 | 22:30 | Wrist consistency fix strategy | 1) body_wins (snap hand to body) 2) hand_wins (snap body to hand) 3) average (midpoint) 4) confidence_weighted (blend by temporal smoothness + dissolve radius) | confidence_weighted with dissolve (option 4) | body_wins causes hard jumps. Confidence-weighted uses smoothness to determine trust, dissolve radius preserves fingertips. Fingertip displacement reduced from 171.7mm to 6.2mm (27.7x improvement). | Completed | changelog: 18.07.2026 22:30
18.07.2026 | 22:30 | Retargeting bone ordering | 1) Sequential (index order) 2) BFS from root joints 3) IK solver (iterative relaxation) | BFS from root joints (option 2) | Sequential ordering caused cascading errors — child bones corrected before parents. BFS guarantees parent bone is set before child. Proportion error reduced from noticeable to ~0. | Completed | changelog: 18.07.2026 22:30
18.07.2026 | 22:30 | Pipeline version numbering | 1) Keep 3.0 for all improvements 2) Increment to 3.1 after problems 15-20 3) Increment to 3.2 after v3.2 improvements | Version 3.2 (option 3) | Distinct versions help track which improvements are included. v3.0 = core pipeline, v3.1 = problems 15-20, v3.2 = 7 pipeline improvements + bug fixes. | Completed | changelog: 18.07.2026 22:30
18.07.2026 | 23:00 | Version control strategy for multi-person development | 1) Copy project folder manually 2) git init + commit + branch 3) No version control, work in-place | Git: init, commit stable v3.2, branch multi-actor-support (option 2) | Manual copy has no diff/rollback granularity. Git provides line-by-line comparison, selective rollback (cherry-pick), and branch isolation. Risk of breaking stable single-actor pipeline is high — need guaranteed rollback point. Branch verified: 13/13 tests pass. | Completed | changelog: 18.07.2026 23:00
18.07.2026 | 23:30 | Multi-person cross-view association approach | 1) Import mvpose directly (Cython + CUDA dependencies) 2) Import multiview_pose geometry utilities 3) Reimplement core algorithms from scratch (epipolar + Hungarian + transitive closure) 4) Use crossview_3d_pose_tracking (rejected: proprietary) | Reimplement from scratch, informed by mvpose (option 3) | mvpose has the best algorithm (SVT + epipolar) with Geometry-only mode (no pretrained weights). But direct import has Cython/CUDA deps. Reimplementation avoids all external dependencies while preserving mathematical rigor. Hungarian matching replaces SVT for simplicity (sufficient for <=6 cameras, <=5 persons). crossview rejected (proprietary), multiview rejected (CNN feature map input incompatible with RTMPose). | Completed | changelog: 18.07.2026 23:30
18.07.2026 | 23:30 | Association algorithm: SVT vs Hungarian matching | 1) SVT semidefinite relaxation (mvpose approach) 2) Hungarian assignment (scipy.optimize.linear_sum_assignment) 3) Greedy nearest-neighbor matching | Hungarian assignment via scipy (option 2) | SVT is mathematically optimal but requires ADMM convergence tuning (alpha, lambda, mu hyperparameters). For our scale (<=6 cameras, <=5 persons), Hungarian gives globally optimal assignment in O(n^3) which is milliseconds. Simpler to implement, debug, and verify. Can upgrade to SVT later if person count grows. | Completed | changelog: 18.07.2026 23:30
18.07.2026 | 18:40 | RTMLib integration: Wholebody class vs direct YOLOX+RTMPose | 1) Use rtmlib Wholebody class (manages YOLOX + RTMPose composition + model URLs automatically) 2) Use YOLOX and RTMPose directly (requires managing ONNX model URLs/paths ourselves) 3) Use ultralytics YOLOv8 for detection + RTMPose for pose | Use rtmlib Wholebody class (option 1) | Wholebody handles model download, URL management, input preprocessing, and bbox-to-pose pipeline. Direct YOLOX/RTMPose requires passing explicit ONNX URLs (discovered: YOLOX.__init__ requires onnx_model arg). Wholebody.__call__ returns (keypoints, scores) for ALL detected persons, which is exactly what multi-person pipeline needs. Simpler, less code, well-tested by rtmlib authors. | Completed | changelog: 18.07.2026 18:40
18.07.2026 | 20:30 | i18n scope: localize only new dual-actor screens vs entire app | A) Localize ONLY new dual-actor screens (bilingual), leave existing FreeMoCap UI English-only B) Localize entire app (50+ files, hundreds of strings) — separate 2-3 day stage C) Introduce i18n infra now, localize new screens + critical path of existing (menus, titles, main buttons) | Option A: localize only new dual-actor screens | Existing FreeMoCap UI is stable (13/13 tests), modifying all strings risks regressions in tested code. New dual-actor screens are self-contained modules that can be built bilingual from scratch. Consistency concern: new screens bilingual, old English-only — accepted tradeoff for this stage. Can upgrade to B later as separate stage. | Accepted | changelog: 18.07.2026 20:30
18.07.2026 | 20:30 | i18n scope for dual-actor UI | A) Localize ONLY new dual-actor screens (bilingual RU/EN), leave existing FreeMoCap UI English-only B) Localize ALL existing FreeMoCap screens (50+ files, hundreds of strings) C) Introduce i18n infrastructure now, localize new screens + critical path of existing (menus, titles, main buttons) | Option A: localize only new dual-actor screens | Smallest scope. Existing FreeMoCap UI (v1.8.2) has zero i18n — all strings hardcoded in PySide6 Python files. Localizing everything (option B) would be a separate 2-3 day effort blocking dual-actor development. Option A accepts visual inconsistency (new bilingual screens vs old EN-only) as a trade-off for shipping dual-actor faster. Can upgrade to B/C later. | Accepted | changelog: 18.07.2026
18.07.2026 | 21:00 | GUI widget architecture for dual-actor screens | A) Standalone QWidget subclasses with signal-based navigation (chosen) B) Subclass FreeMoCap MainWindow directly C) Use QML for new screens | Option A: Standalone QWidget subclasses | Widget subclasses are composable, testable in isolation (57/57 headless tests), and don't require modifying FreeMoCap internals. Signal-based navigation (mode_selected, continue_clicked, back_clicked) allows parent to control flow without tight coupling. QML (C) rejected: PySide6 QML integration adds complexity, team familiarity unknown. MainWindow subclass (B) rejected: would require modifying FreeMoCap package files, breaks rollback guarantee. | Accepted | changelog: 18.07.2026